## Executive Summary
Field | Value
Sprint name | Hosted QA Cycle 1 - Strict 7-Day Execution
QA start date/time | 2026-06-10 09:00 IST
Planned completion date/time | 2026-06-16 18:00 IST
Final QA submission date/time | 2026-06-16 18:00 IST
Active shared hosted QA/staging frontend | https://hawkaii-hrms.vercel.app
Active shared hosted QA/staging API | https://hawkaii-hrms-dev-gyvr.onrender.com
Future production frontend/API | https://hawkaii.in / https://api.hawkaii.in (setup required until live)
Future QA frontend/API | https://qa.hawkaii.in / https://qa-api.hawkaii.in (setup required until live)
Future hosted dev frontend/API | https://dev.hawkaii.in / https://dev-api.hawkaii.in (setup required until live)
Production destructive testing | Disabled unless safe test tenant and reset process are documented
Total executable cases | 51
Priority distribution | P0 28 / P1 16 / P2 7
Release recommendation rule | Any failed P0 is No-Go unless explicitly waived; P0 setup-required is Conditional Go or No-Go

## How To Use
Step | Instruction
1 | Execute only rows assigned to the current Execution Day unless the QA Lead reassigns them.
2 | Submit each day evidence and status by 20:00 IST; Day 7 final signoff package is due by 18:00 IST.
3 | Use the current shared hosted QA/staging frontend and API for execution unless a row is explicitly marked future-domain setup required.
4 | Keep Actual Result factual and attach screenshot, API response/request ID, export file, email/notification, or document URL.
5 | Mark Blocked or Setup Required with owner and next action; do not silently skip rows.
6 | Production create/update/delete testing is disabled unless a safe production test tenant and reset process are documented.

## Environment Matrix
Environment | Status for this cycle | Frontend | API | Allowed read-only discovery | Allowed create/update/delete | Branch | Notes | Submission handling
Current Shared Hosted QA/Staging | Active execution target | https://hawkaii-hrms.vercel.app | https://hawkaii-hrms-dev-gyvr.onrender.com | Yes | Yes, QA/staging test data only | Current deployed branch | Vercel and Render are shared for first hosted QA cycle. | Daily evidence due by assigned cutoff
Future Production | Setup Required | https://hawkaii.in | https://api.hawkaii.in | Read-only only after live | No, unless safe tenant/reset is documented | main | Do not pretend this is isolated until service is live. | Track as setup-required blocker
Future QA/UAT | Setup Required | https://qa.hawkaii.in | https://qa-api.hawkaii.in | Yes after live | Yes after live and seeded safely | qa | Future isolated QA target. | Track as setup-required blocker
Future Hosted Dev | Setup Required | https://dev.hawkaii.in | https://dev-api.hawkaii.in | Yes after live | Yes after live and seeded safely | dev | Future isolated hosted dev target. | Track as setup-required blocker
Local Dev | Out of hosted QA scope | Local frontend | Local API | Optional developer verification | Local only | feature/local | Not the first hosted QA execution target. | Not part of client submission

## Agile Sprint Plan
Day | Date | Testing Scope | Required Evidence | Completion Owner | Reviewer | Submission Due | Exit Criteria | Story Points | Cases
Day 1 | 2026-06-10 | P0 gate and shared hosted environment readiness | Screenshots, request IDs/API response, export file, email/notification, document URL as applicable | QA Lead | Release Manager | 2026-06-10 20:00 IST | All assigned P0/P1 executed or explicitly blocked with owner and next action | 18 | 12
Day 2 | 2026-06-11 | HR core workflows | Screenshots, request IDs/API response, export file, email/notification, document URL as applicable | Assigned QA Tester | QA Lead | 2026-06-11 20:00 IST | All assigned P0/P1 executed or explicitly blocked with owner and next action | 13 | 5
Day 3 | 2026-06-12 | Expense, documents, and media | Screenshots, request IDs/API response, export file, email/notification, document URL as applicable | Assigned QA Tester | QA Lead | 2026-06-12 20:00 IST | All assigned P0/P1 executed or explicitly blocked with owner and next action | 15 | 5
Day 4 | 2026-06-13 | Projects, assets, helpdesk, and notifications | Screenshots, request IDs/API response, export file, email/notification, document URL as applicable | Assigned QA Tester | QA Lead | 2026-06-13 20:00 IST | All assigned P0/P1 executed or explicitly blocked with owner and next action | 11 | 4
Day 5 | 2026-06-14 | Reports, admin policies, and business rules | Screenshots, request IDs/API response, export file, email/notification, document URL as applicable | Assigned QA Tester | QA Lead | 2026-06-14 20:00 IST | All assigned P0/P1 executed or explicitly blocked with owner and next action | 9 | 6
Day 6 | 2026-06-15 | Full regression, cross-browser, and deployment checks | Screenshots, request IDs/API response, export file, email/notification, document URL as applicable | Assigned QA Tester | QA Lead | 2026-06-15 20:00 IST | All assigned P0/P1 executed or explicitly blocked with owner and next action | 19 | 17
Day 7 | 2026-06-16 | Defect retest and final QA submission | Screenshots, request IDs/API response, export file, email/notification, document URL as applicable | QA Lead | Release Manager | 2026-06-16 18:00 IST | All assigned P0/P1 executed or explicitly blocked with owner and next action | 3 | 2

## Main Test Cases
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
AUTH-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | P0 Release Gate | P0 | 2 | Release Gate P0 | Auth | Login, session refresh, logout | BLQ-017 | High | Happy Path / Security | Employee/Admin | QA | User exists | Seeded QA users | Login, refresh page, call /me, logout, refresh. | Session persists only while valid and logout clears access. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
AUTH-P0-002 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | P0 Release Gate | P0 | 2 | Release Gate P0 | Email Verification | QA/prod explicit confirm | BLQ-016 | High | Security | New user | QA/Production | Verification email received | Verification link | Open verification link; verify no auto-submit; click confirm. | Verification happens only after explicit user action. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ONB-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | P0 Release Gate | P0 | 2 | Release Gate P0 | Onboarding | New workspace empty state | BLQ-024 | High | Data Isolation | Admin | QA | Fresh workspace | New company | Bootstrap company and open dashboard/modules. | Only empty org-scoped real data appears. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
RBAC-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P0 | 2 | Release Gate P0 | RBAC | Key role navigation and backend denial | BLQ-001/017 | High | Permission | Employee/Manager/Admin | QA | Users with roles | Role accounts | Check sidebar then call one forbidden API directly. | UI hides unauthorized actions and backend returns forbidden. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ATT-P0-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P0 | 3 | Release Gate P0 | Attendance | Punch, break, punch out | BLQ-005/006 | High | Happy Path | Employee | QA | Attendance policy active | Employee user | Punch in, start/end break, punch out. | Today totals and status update from backend. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EXP-P0-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Finance | QA Lead | Finance/Expense Regression | P0 | 5 | Release Gate P0 | Expenses | Requester to Manager to Finance settlement | BLQ-002/003 | High | Multi-role E2E | Employee/Manager/Finance Manager | QA | Routing configured | Expense ticket | Submit expense, manager verify, finance approve, pay, settle. | Ticket closes through v1 flow without Director stage. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EXP-P0-002 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Finance | QA Lead | Finance/Expense Regression | P0 | 2 | Release Gate P0 | Expenses | Self-processing blocked | BLQ-002 | High | Negative | Admin/Manager/Finance Manager | QA | Requester has workflow role | Own expense | Try manager/finance/payment action on own expense. | Backend blocks self-processing. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
DOC-P0-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Documents | QA Lead | Documents/Media Regression | P0 | 3 | Release Gate P0 | Documents | Upload/open/delete | BLQ-013/015 | High | Storage | Admin/Employee | QA | Cloudinary real storage | PDF/image | Upload document, open download URL, delete with custom confirmation. | File persists in Cloudinary and deletion matches current hard-delete rule. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
CFG-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 2 | Release Gate P0 | Config | Cloudinary and API mocks disabled | BLQ-015/024 | High | Config | QA Lead | QA/Production | Env access | Hosted env | Inspect app behavior and env dashboard values. | Hosted QA/prod use real API and real Cloudinary. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
RPT-P0-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Reports | QA Lead | Reports/Export Regression | P0 | 1 | Release Gate P0 | Reports | Basic report/export handoff | BLQ-020 | Medium | Happy Path | Admin/Finance Manager | QA | Report data exists | Expense register | Open report and trigger export/download. | Export handoff works or clear empty state appears. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
MOB-P0-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Compatibility | QA Lead | Mobile/Cross-Browser Regression | P0 | 1 | Release Gate P0 | Mobile | Employee-critical mobile smoke | BLQ-025 | Medium | Mobile | Employee | QA | Mobile viewport | Employee user | Login, dashboard, attendance, expense/helpdesk quick checks. | Critical employee flows usable on mobile. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
DEP-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Deployment Smoke | P0 | 1 | Deployment Smoke | Backend | Current shared hosted QA/staging API health | DEP-API | High | Smoke | QA Lead | Shared QA/Staging | Service deployed | https://hawkaii-hrms-dev-gyvr.onrender.com/api/v1/health/ready | Open API health endpoint; capture status, response body, and request ID if available. | Current shared Render API responds successfully without exposing secrets. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes | Current execution target, not an isolated production API.
DEP-P0-002 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Backend | Future QA API health | DEP-API | High | Smoke | QA Lead | Future QA | Service deployed | https://qa-api.hawkaii.in | GET /api/v1/health/ready. | 200 response shows app_env qa. | Setup Required |  | Screenshot/API response/request_id |  |  | Future QA API domain qa-api.hawkaii.in is not live; use the current shared Render API for this QA cycle. | 2026-06-16 | Setup Required | Yes
DEP-P0-003 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Backend | Future hosted dev API health | DEP-API | Medium | Smoke | QA Lead | Future Hosted Dev | Service deployed | https://dev-api.hawkaii.in | GET /api/v1/health/ready. | 200 response shows app_env development. | Setup Required |  | Screenshot/API response/request_id |  |  | Future hosted dev API domain dev-api.hawkaii.in is not live. | 2026-06-16 | Setup Required | Yes
DEP-P0-004 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Deployment Smoke | P0 | 1 | Deployment Smoke | Frontend | Current shared hosted QA/staging frontend loads | DEP-FE | High | Smoke | QA Lead | Shared QA/Staging | Frontend deployed | https://hawkaii-hrms.vercel.app | Open frontend URL; confirm login page/app shell loads over HTTPS. | Current shared Vercel frontend loads without mixed-content or availability errors. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes | Current execution target, not an isolated production frontend.
DEP-P0-005 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Frontend | Future QA/dev environment banner checks | DEP-FE | Medium | UI State | QA Lead | Future QA/Future Hosted Dev | Frontend deployed | https://qa.hawkaii.in and https://dev.hawkaii.in | Open QA and dev frontends. | QA/dev environment banner visible; production has no distracting banner. | Setup Required |  | Screenshot/API response/request_id |  |  | Future QA and hosted dev frontend domains are not live. | 2026-06-16 | Setup Required | Yes
DEP-P0-006 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Worker | Render worker starts | DEP-WORKER | High | Smoke | Release Owner | QA/Production | Render access | Worker logs | Inspect worker latest deploy logs. | Worker starts and connects to DB/Valkey. | Setup Required |  | Screenshot/API response/request_id |  |  | Isolated QA/production Render worker evidence is not available for this shared hosted QA cycle. | 2026-06-16 | Setup Required | Yes
CICD-P0-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | PR checks no deploy | DEP-CICD | High | CI | Developer | GitHub | PR open | PR to dev/qa/main | Open PR and observe workflow. | Checks run; no deploy hooks fire. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
CICD-P0-002 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | dev branch deploy | DEP-CICD | High | CI | Developer | GitHub | Secrets set | dev branch | Push to dev. | Hosted dev deploy hook triggers after checks pass. | Setup Required |  | Screenshot/API response/request_id |  |  | Hosted dev branch deployment target is not live as an isolated service. | 2026-06-16 | Setup Required | Yes
CICD-P0-003 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | qa branch deploy | DEP-CICD | High | CI | Developer | GitHub | Secrets set | qa branch | Push to qa. | QA deploy hook triggers after checks pass. | Setup Required |  | Screenshot/API response/request_id |  |  | QA branch deployment target is not live as an isolated service. | 2026-06-16 | Setup Required | Yes
CICD-P0-004 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | production approval | DEP-CICD | High | CI/Security | Release Owner | GitHub | Environment protection configured | main branch | Push to main. | Production deploy waits for configured approval. | Setup Required |  | Screenshot/API response/request_id |  |  | Production environment approval and production deploy target require dashboard configuration evidence. | 2026-06-16 | Setup Required | Yes
CICD-P0-005 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | missing secret failure | DEP-CICD | Medium | Negative | Release Owner | GitHub | Safe test repo/env | Unset deploy hook | Run workflow with missing deploy hook. | Workflow fails clearly before attempting deployment. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
DNS-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Domain DNS SSL CORS | DNS/SSL | Production DNS and certificate | DEP-DNS | High | Network | QA Lead | Future Production | DNS configured | https://hawkaii.in and https://api.hawkaii.in | Resolve hosts and open HTTPS URLs. | Certificates valid and pages/API reachable. | Setup Required |  | Screenshot/API response/request_id |  |  | Future production hawkaii.in and api.hawkaii.in DNS/certificate setup is not live. | 2026-06-16 | Setup Required | Yes
DNS-P0-002 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Domain DNS SSL CORS | CORS/Cookies | Prod frontend to API | DEP-CORS | High | Security | QA Lead | Future Production | API and frontend live | https://hawkaii.in -> https://api.hawkaii.in | Login from hawkaii.in and inspect API calls. | Credentials work only against api.hawkaii.in. | Setup Required |  | Screenshot/API response/request_id |  |  | Future production frontend/API domain pair is not live for CORS/cookie validation. | 2026-06-16 | Setup Required | Yes
DNS-P0-003 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P0 | 1 | Domain DNS SSL CORS | CORS/Cookies | Cross-env cookie isolation | DEP-CORS | High | Security | QA Lead | Future QA/Future Production | Both envs live | https://qa.hawkaii.in and https://hawkaii.in | Login QA, then open prod and call /me. | QA session is not accepted by production. | Setup Required |  | Screenshot/API response/request_id |  |  | Future QA/production domain isolation is not live. | 2026-06-16 | Setup Required | Yes
DATA-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Data Isolation | Neon | Separate DB connection strings | DEP-DATA | High | Data Isolation | Release Owner | Future Dev/QA/Production | Dashboard access | Render env | Compare DATABASE_URL branch names/endpoints. | Dev, QA, production point to different Neon branches/endpoints. | Setup Required |  | Screenshot/API response/request_id |  |  | Separate dev, QA, and production database connection evidence is required before isolated environment testing. | 2026-06-16 | Setup Required | Yes
DATA-P0-002 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Data Isolation | Valkey | Separate Valkey instances | DEP-VALKEY | High | Data Isolation | Release Owner | Future Dev/QA/Production | Render access | Render services | Compare VALKEY_URL source service per env. | Each env uses its own Render Key Value service. | Setup Required |  | Screenshot/API response/request_id |  |  | Separate dev, QA, and production Valkey evidence is required before isolated environment testing. | 2026-06-16 | Setup Required | Yes
SEC-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 2 | Secrets Config Checklist | Secrets | Prod secret readiness | DEP-SECRETS | High | Config | Release Owner | Future Production | Dashboard access | Render/GitHub/Cloudflare | Inspect required production secrets and weak placeholder values. | No default secrets or placeholders are used. | Setup Required |  | Screenshot/API response/request_id |  |  | Production secret readiness requires production dashboard evidence; no production destructive testing is allowed. | 2026-06-16 | Setup Required | Yes
SEC-P1-002 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P1 | 1 | Secrets Config Checklist | OpenAPI | Docs exposure setting | BLQ-023 | Medium | Security | Release Owner | Future Production | OPENAPI_PUBLIC configured | /docs | Open docs/openapi URLs. | Exposure matches approved setting. | Setup Required |  | Screenshot/API response/request_id |  |  | Production OpenAPI exposure check requires the future production API domain to be live. | 2026-06-16 | Setup Required | Yes
BRANCH-P1-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P1 | 1 | Branch Promotion Matrix | Branching | Feature to dev promotion | DEP-BRANCH | Medium | Process | Developer | GitHub | Feature branch exists | PR | Open PR to dev and merge after checks. | Hosted dev deployment follows merge. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
BRANCH-P1-002 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P1 | 1 | Branch Promotion Matrix | Branching | QA to production promotion | DEP-BRANCH | High | Process | Release Owner | GitHub | QA signed off | PR to main | Promote QA-approved changes to main. | Production deploy only after approval. | Setup Required |  | Screenshot/API response/request_id |  |  | QA to production promotion cannot be validated until the production target and approval process are configured. | 2026-06-16 | Setup Required | Yes
EMP-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 3 | Sprint Regression | Employees | Employee CRUD and profile photo | BLQ-001/015 | High | Regression | Admin/HR Manager | QA | Admin user | Employee data/image | Create/update employee and upload profile photo. | Backend persists employee and Cloudinary image. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EMS-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 2 | Sprint Regression | EMS | My profile and documents | BLQ-021 | Medium | Regression | Employee | QA | Employee user | Profile data | Open EMS profile, update allowed fields, upload/view document. | Accepted fields save; rejected fields show backend message. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
LEAVE-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 3 | Sprint Regression | Leave/WFH | Leave request lifecycle | BLQ-008/009 | High | Regression | Employee/Manager/HR | QA | Leave policy configured | Leave request | Submit, approve/return/cancel as applicable. | Lifecycle follows backend policy and balances display. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
TIME-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 2 | Sprint Regression | Timesheets | Submit under/over warning | BLQ-010 | Medium | Regression | Employee/Manager | QA | Project assignment | Timesheet | Submit normal and under/over week. | Backend acceptance/warnings match policy. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ADM-P1-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Admin Settings | Settings save and refresh | BLQ-004 | High | Regression | Admin | QA | Admin user | Workflow/policy settings | Change settings, save, refresh. | Persisted settings reload correctly; runtime effect tested only where proven. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
NOTIF-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 2 | Sprint Regression | Notifications | Unread/read/read all | BLQ-019 | Medium | Regression | Employee/Admin | QA | Notifications exist | Notification feed | Open feed, mark one read, mark all read. | Counts and user scoping are correct. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
PROJ-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Projects | Cost center and over-allocation ack | BLQ-011/012 | High | Regression | Admin/Project Manager | QA | Project and department setup | Allocation >100% | Select department, create allocation over 100 with acknowledgement. | Cost center autofills when configured; over-allocation requires explicit ack. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EXP-P1-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Finance | QA Lead | Finance/Expense Regression | P1 | 3 | Sprint Regression | Expenses | Return/reject/clarification | BLQ-002/003 | High | Regression | Manager/Finance Manager/Employee | QA | Expense exists | Expense ticket | Return, resubmit, reject, add clarification. | Status and audit timeline update once without duplicate entries. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
DOC-P1-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Documents | QA Lead | Documents/Media Regression | P1 | 2 | Sprint Regression | Documents | File validation | BLQ-013/015 | Medium | Negative | Employee/Admin | QA | Upload policy available | Oversize/wrong MIME | Upload invalid files. | Backend rejects with friendly message. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
RPT-P1-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Reports | QA Lead | Reports/Export Regression | P1 | 2 | Sprint Regression | Reports | Reports by role | BLQ-020 | Medium | Regression | Admin/Auditor/Finance Manager | QA | Report data | Report filters | Open each role report and export where allowed. | Allowed reports load; forbidden reports are blocked. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
HELP-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Helpdesk | Ticket lifecycle | BLQ-018 | Medium | Regression | Employee/Admin | QA | Helpdesk categories | Ticket | Create, comment, assign/status, resolve/reopen. | Status, comments, attachments, SLA values follow API. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ASSET-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Assets | Assignment/return/recovery | BLQ-022 | Medium | Regression | Asset Manager/Admin/Employee | QA | Asset inventory | Asset | Assign asset, return, process recovery settlement. | Current recovery behavior works; payroll deduction remains future scope. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
AUTH-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P2 | 1 | Full Regression | Auth | Expired/used verification token | BLQ-016 | Medium | Edge | New user | QA | Token variants | Expired/used token | Open invalid token and confirm. | User-friendly error and no account verification. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
ATT-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P2 | 2 | Full Regression | Attendance | Cross-midnight work date | BLQ-007 | Medium | Edge | Employee | QA | Policy permits | Cross-midnight punch | Punch before midnight and out after midnight. | Record assigned to check-in work date in user timezone. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
HOL-P2-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P2 | 1 | Full Regression | Holidays | Global and optional holidays | BLQ-009 | Low | Edge | Employee/HR | QA | Holiday data | All/optional holiday | Open holiday calendar and leave request around holiday. | All region is global; optional is display-only unless backend proves more. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
DOC-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Documents | QA Lead | Documents/Media Regression | P2 | 1 | Full Regression | Documents | Download after delete | BLQ-013 | Medium | Negative | Admin | QA | Deleted document | Document ID | Try download after confirmed delete. | Fails cleanly without orphaned metadata. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
SEC-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P2 | 1 | Full Regression | Security | Production docs exposure | BLQ-023 | Medium | Security | QA Lead | Future Production | OPENAPI_PUBLIC=false | /docs URL | Open /docs and /api/v1/openapi.json. | Production does not expose docs unless intentionally configured. | Setup Required |  | Screenshot/API response/request_id |  |  | Production docs exposure check requires the future production API domain to be live. |  | Setup Required | Yes
MOB-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Compatibility | QA Lead | Mobile/Cross-Browser Regression | P2 | 2 | Full Regression | Mobile | Admin table overflow | BLQ-025 | Low | Responsive | Admin | QA | Mobile viewport | Admin-heavy tables | Open employees/reports/admin tables on mobile. | No critical overlap; admin-heavy tables remain usable or documented. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
ROLL-P1-001 | Hosted QA Cycle 1 | Day 7 | 2026-06-16 | 2026-06-16 | 2026-06-16 18:00 IST | 2026-06-16 18:00 IST | QA Lead | Product Owner | Defect Retest / Final Signoff | P1 | 2 | Rollback Checklist | Rollback | Render backend rollback | DEP-ROLLBACK | High | Process | Release Owner | QA/Production | Prior deploy exists | Render deploy | Use rollback runbook on non-prod drill. | Previous API deploy restored and health passes. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ROLL-P2-002 | Hosted QA Cycle 1 | Day 7 | 2026-06-16 | 2026-06-16 | 2026-06-16 18:00 IST | 2026-06-16 18:00 IST | QA Lead | Product Owner | Defect Retest / Final Signoff | P2 | 1 | Rollback Checklist | Rollback | Frontend rollback | DEP-ROLLBACK | Medium | Process | Release Owner | QA | Cloudflare history exists | Frontend deploy | Rollback QA frontend to previous deploy. | Frontend loads previous working version. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes

## Execution Summary
Metric | Value | Notes
Sprint name | Hosted QA Cycle 1 | Strict first full hosted QA cycle
Planned QA start date | 2026-06-10 | 09:00 IST
Planned completion date | 2026-06-16 | Execution closes at 18:00 IST on final day
Final submission date/time | 2026-06-16 18:00 IST | Final signoff package due
Active frontend | https://hawkaii-hrms.vercel.app | Shared hosted QA/staging
Active API | https://hawkaii-hrms-dev-gyvr.onrender.com | Shared hosted QA/staging
Total cases | 51 | Executable workbook cases
Total P0 | 28 | Release/client signoff blockers
Total P1 | 16 | Important regression
Total P2 | 7 | Lower-risk/future readiness/deep regression
Completed | 0 | No execution evidence submitted yet
Passed | 0 | Updated during execution
Failed | 0 | Updated during execution
Blocked | 16 | Includes setup-required future-domain/environment checks
Not run | 35 | Awaiting assigned execution day
P0 pass rate | 0% | No P0 execution completed yet
P1 pass rate | 0% | No P1 execution completed yet
Release recommendation | Conditional Go | Go is not allowed while P0 setup-required items remain open
Open risk summary | Future domain and isolated environment checks remain setup-required; execute release gate on current shared hosted QA/staging only. | No production destructive testing without safe tenant/reset
Signoff owner | Product Owner / Release Manager | Final signoff owner
Signoff date | 2026-06-16 | Target signoff date

## Release Gates
Gate | Rule | Owner | Status
P0 release gate | Every executable P0 must pass or be explicitly waived; failed P0 is No-Go. | QA Lead / Release Manager | Not Run
Future environment gate | Future-domain and isolated-environment rows remain Setup Required until live evidence exists. | Release Manager | Setup Required
Production safety gate | No production create/update/delete without safe tenant and reset process. | Release Manager | Active
Final submission gate | Final package due 2026-06-16 18:00 IST. | QA Lead | Not Run

## P0 Smoke UAT Gate
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
AUTH-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | P0 Release Gate | P0 | 2 | Release Gate P0 | Auth | Login, session refresh, logout | BLQ-017 | High | Happy Path / Security | Employee/Admin | QA | User exists | Seeded QA users | Login, refresh page, call /me, logout, refresh. | Session persists only while valid and logout clears access. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
AUTH-P0-002 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | P0 Release Gate | P0 | 2 | Release Gate P0 | Email Verification | QA/prod explicit confirm | BLQ-016 | High | Security | New user | QA/Production | Verification email received | Verification link | Open verification link; verify no auto-submit; click confirm. | Verification happens only after explicit user action. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ONB-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | P0 Release Gate | P0 | 2 | Release Gate P0 | Onboarding | New workspace empty state | BLQ-024 | High | Data Isolation | Admin | QA | Fresh workspace | New company | Bootstrap company and open dashboard/modules. | Only empty org-scoped real data appears. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
RBAC-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P0 | 2 | Release Gate P0 | RBAC | Key role navigation and backend denial | BLQ-001/017 | High | Permission | Employee/Manager/Admin | QA | Users with roles | Role accounts | Check sidebar then call one forbidden API directly. | UI hides unauthorized actions and backend returns forbidden. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ATT-P0-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P0 | 3 | Release Gate P0 | Attendance | Punch, break, punch out | BLQ-005/006 | High | Happy Path | Employee | QA | Attendance policy active | Employee user | Punch in, start/end break, punch out. | Today totals and status update from backend. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EXP-P0-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Finance | QA Lead | Finance/Expense Regression | P0 | 5 | Release Gate P0 | Expenses | Requester to Manager to Finance settlement | BLQ-002/003 | High | Multi-role E2E | Employee/Manager/Finance Manager | QA | Routing configured | Expense ticket | Submit expense, manager verify, finance approve, pay, settle. | Ticket closes through v1 flow without Director stage. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EXP-P0-002 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Finance | QA Lead | Finance/Expense Regression | P0 | 2 | Release Gate P0 | Expenses | Self-processing blocked | BLQ-002 | High | Negative | Admin/Manager/Finance Manager | QA | Requester has workflow role | Own expense | Try manager/finance/payment action on own expense. | Backend blocks self-processing. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
DOC-P0-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Documents | QA Lead | Documents/Media Regression | P0 | 3 | Release Gate P0 | Documents | Upload/open/delete | BLQ-013/015 | High | Storage | Admin/Employee | QA | Cloudinary real storage | PDF/image | Upload document, open download URL, delete with custom confirmation. | File persists in Cloudinary and deletion matches current hard-delete rule. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
CFG-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 2 | Release Gate P0 | Config | Cloudinary and API mocks disabled | BLQ-015/024 | High | Config | QA Lead | QA/Production | Env access | Hosted env | Inspect app behavior and env dashboard values. | Hosted QA/prod use real API and real Cloudinary. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
RPT-P0-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Reports | QA Lead | Reports/Export Regression | P0 | 1 | Release Gate P0 | Reports | Basic report/export handoff | BLQ-020 | Medium | Happy Path | Admin/Finance Manager | QA | Report data exists | Expense register | Open report and trigger export/download. | Export handoff works or clear empty state appears. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
MOB-P0-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Compatibility | QA Lead | Mobile/Cross-Browser Regression | P0 | 1 | Release Gate P0 | Mobile | Employee-critical mobile smoke | BLQ-025 | Medium | Mobile | Employee | QA | Mobile viewport | Employee user | Login, dashboard, attendance, expense/helpdesk quick checks. | Critical employee flows usable on mobile. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes

## Deployment Smoke
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
DEP-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Deployment Smoke | P0 | 1 | Deployment Smoke | Backend | Current shared hosted QA/staging API health | DEP-API | High | Smoke | QA Lead | Shared QA/Staging | Service deployed | https://hawkaii-hrms-dev-gyvr.onrender.com/api/v1/health/ready | Open API health endpoint; capture status, response body, and request ID if available. | Current shared Render API responds successfully without exposing secrets. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes | Current execution target, not an isolated production API.
DEP-P0-002 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Backend | Future QA API health | DEP-API | High | Smoke | QA Lead | Future QA | Service deployed | https://qa-api.hawkaii.in | GET /api/v1/health/ready. | 200 response shows app_env qa. | Setup Required |  | Screenshot/API response/request_id |  |  | Future QA API domain qa-api.hawkaii.in is not live; use the current shared Render API for this QA cycle. | 2026-06-16 | Setup Required | Yes
DEP-P0-003 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Backend | Future hosted dev API health | DEP-API | Medium | Smoke | QA Lead | Future Hosted Dev | Service deployed | https://dev-api.hawkaii.in | GET /api/v1/health/ready. | 200 response shows app_env development. | Setup Required |  | Screenshot/API response/request_id |  |  | Future hosted dev API domain dev-api.hawkaii.in is not live. | 2026-06-16 | Setup Required | Yes
DEP-P0-004 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Deployment Smoke | P0 | 1 | Deployment Smoke | Frontend | Current shared hosted QA/staging frontend loads | DEP-FE | High | Smoke | QA Lead | Shared QA/Staging | Frontend deployed | https://hawkaii-hrms.vercel.app | Open frontend URL; confirm login page/app shell loads over HTTPS. | Current shared Vercel frontend loads without mixed-content or availability errors. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes | Current execution target, not an isolated production frontend.
DEP-P0-005 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Frontend | Future QA/dev environment banner checks | DEP-FE | Medium | UI State | QA Lead | Future QA/Future Hosted Dev | Frontend deployed | https://qa.hawkaii.in and https://dev.hawkaii.in | Open QA and dev frontends. | QA/dev environment banner visible; production has no distracting banner. | Setup Required |  | Screenshot/API response/request_id |  |  | Future QA and hosted dev frontend domains are not live. | 2026-06-16 | Setup Required | Yes
DEP-P0-006 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Deployment Smoke | Worker | Render worker starts | DEP-WORKER | High | Smoke | Release Owner | QA/Production | Render access | Worker logs | Inspect worker latest deploy logs. | Worker starts and connects to DB/Valkey. | Setup Required |  | Screenshot/API response/request_id |  |  | Isolated QA/production Render worker evidence is not available for this shared hosted QA cycle. | 2026-06-16 | Setup Required | Yes

## CI-CD Validation
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
CICD-P0-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | PR checks no deploy | DEP-CICD | High | CI | Developer | GitHub | PR open | PR to dev/qa/main | Open PR and observe workflow. | Checks run; no deploy hooks fire. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
CICD-P0-002 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | dev branch deploy | DEP-CICD | High | CI | Developer | GitHub | Secrets set | dev branch | Push to dev. | Hosted dev deploy hook triggers after checks pass. | Setup Required |  | Screenshot/API response/request_id |  |  | Hosted dev branch deployment target is not live as an isolated service. | 2026-06-16 | Setup Required | Yes
CICD-P0-003 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | qa branch deploy | DEP-CICD | High | CI | Developer | GitHub | Secrets set | qa branch | Push to qa. | QA deploy hook triggers after checks pass. | Setup Required |  | Screenshot/API response/request_id |  |  | QA branch deployment target is not live as an isolated service. | 2026-06-16 | Setup Required | Yes
CICD-P0-004 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | production approval | DEP-CICD | High | CI/Security | Release Owner | GitHub | Environment protection configured | main branch | Push to main. | Production deploy waits for configured approval. | Setup Required |  | Screenshot/API response/request_id |  |  | Production environment approval and production deploy target require dashboard configuration evidence. | 2026-06-16 | Setup Required | Yes
CICD-P0-005 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | CI-CD Validation | GitHub Actions | missing secret failure | DEP-CICD | Medium | Negative | Release Owner | GitHub | Safe test repo/env | Unset deploy hook | Run workflow with missing deploy hook. | Workflow fails clearly before attempting deployment. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes

## Domain DNS SSL CORS
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
DNS-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Domain DNS SSL CORS | DNS/SSL | Production DNS and certificate | DEP-DNS | High | Network | QA Lead | Future Production | DNS configured | https://hawkaii.in and https://api.hawkaii.in | Resolve hosts and open HTTPS URLs. | Certificates valid and pages/API reachable. | Setup Required |  | Screenshot/API response/request_id |  |  | Future production hawkaii.in and api.hawkaii.in DNS/certificate setup is not live. | 2026-06-16 | Setup Required | Yes
DNS-P0-002 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Domain DNS SSL CORS | CORS/Cookies | Prod frontend to API | DEP-CORS | High | Security | QA Lead | Future Production | API and frontend live | https://hawkaii.in -> https://api.hawkaii.in | Login from hawkaii.in and inspect API calls. | Credentials work only against api.hawkaii.in. | Setup Required |  | Screenshot/API response/request_id |  |  | Future production frontend/API domain pair is not live for CORS/cookie validation. | 2026-06-16 | Setup Required | Yes
DNS-P0-003 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P0 | 1 | Domain DNS SSL CORS | CORS/Cookies | Cross-env cookie isolation | DEP-CORS | High | Security | QA Lead | Future QA/Future Production | Both envs live | https://qa.hawkaii.in and https://hawkaii.in | Login QA, then open prod and call /me. | QA session is not accepted by production. | Setup Required |  | Screenshot/API response/request_id |  |  | Future QA/production domain isolation is not live. | 2026-06-16 | Setup Required | Yes

## Data Isolation
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
DATA-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Data Isolation | Neon | Separate DB connection strings | DEP-DATA | High | Data Isolation | Release Owner | Future Dev/QA/Production | Dashboard access | Render env | Compare DATABASE_URL branch names/endpoints. | Dev, QA, production point to different Neon branches/endpoints. | Setup Required |  | Screenshot/API response/request_id |  |  | Separate dev, QA, and production database connection evidence is required before isolated environment testing. | 2026-06-16 | Setup Required | Yes
DATA-P0-002 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 1 | Data Isolation | Valkey | Separate Valkey instances | DEP-VALKEY | High | Data Isolation | Release Owner | Future Dev/QA/Production | Render access | Render services | Compare VALKEY_URL source service per env. | Each env uses its own Render Key Value service. | Setup Required |  | Screenshot/API response/request_id |  |  | Separate dev, QA, and production Valkey evidence is required before isolated environment testing. | 2026-06-16 | Setup Required | Yes

## Secrets Config Checklist
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
SEC-P0-001 | Hosted QA Cycle 1 | Day 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P0 | 2 | Secrets Config Checklist | Secrets | Prod secret readiness | DEP-SECRETS | High | Config | Release Owner | Future Production | Dashboard access | Render/GitHub/Cloudflare | Inspect required production secrets and weak placeholder values. | No default secrets or placeholders are used. | Setup Required |  | Screenshot/API response/request_id |  |  | Production secret readiness requires production dashboard evidence; no production destructive testing is allowed. | 2026-06-16 | Setup Required | Yes
SEC-P1-002 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P1 | 1 | Secrets Config Checklist | OpenAPI | Docs exposure setting | BLQ-023 | Medium | Security | Release Owner | Future Production | OPENAPI_PUBLIC configured | /docs | Open docs/openapi URLs. | Exposure matches approved setting. | Setup Required |  | Screenshot/API response/request_id |  |  | Production OpenAPI exposure check requires the future production API domain to be live. | 2026-06-16 | Setup Required | Yes

## Branch Promotion Matrix
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
BRANCH-P1-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P1 | 1 | Branch Promotion Matrix | Branching | Feature to dev promotion | DEP-BRANCH | Medium | Process | Developer | GitHub | Feature branch exists | PR | Open PR to dev and merge after checks. | Hosted dev deployment follows merge. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
BRANCH-P1-002 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | Release Manager | QA Lead | CI-CD/Environment Readiness | P1 | 1 | Branch Promotion Matrix | Branching | QA to production promotion | DEP-BRANCH | High | Process | Release Owner | GitHub | QA signed off | PR to main | Promote QA-approved changes to main. | Production deploy only after approval. | Setup Required |  | Screenshot/API response/request_id |  |  | QA to production promotion cannot be validated until the production target and approval process are configured. | 2026-06-16 | Setup Required | Yes

## Sprint Regression
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
EMP-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 3 | Sprint Regression | Employees | Employee CRUD and profile photo | BLQ-001/015 | High | Regression | Admin/HR Manager | QA | Admin user | Employee data/image | Create/update employee and upload profile photo. | Backend persists employee and Cloudinary image. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EMS-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 2 | Sprint Regression | EMS | My profile and documents | BLQ-021 | Medium | Regression | Employee | QA | Employee user | Profile data | Open EMS profile, update allowed fields, upload/view document. | Accepted fields save; rejected fields show backend message. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
LEAVE-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 3 | Sprint Regression | Leave/WFH | Leave request lifecycle | BLQ-008/009 | High | Regression | Employee/Manager/HR | QA | Leave policy configured | Leave request | Submit, approve/return/cancel as applicable. | Lifecycle follows backend policy and balances display. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
TIME-P1-001 | Hosted QA Cycle 1 | Day 2 | 2026-06-11 | 2026-06-11 | 2026-06-11 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P1 | 2 | Sprint Regression | Timesheets | Submit under/over warning | BLQ-010 | Medium | Regression | Employee/Manager | QA | Project assignment | Timesheet | Submit normal and under/over week. | Backend acceptance/warnings match policy. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ADM-P1-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Admin Settings | Settings save and refresh | BLQ-004 | High | Regression | Admin | QA | Admin user | Workflow/policy settings | Change settings, save, refresh. | Persisted settings reload correctly; runtime effect tested only where proven. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
NOTIF-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 2 | Sprint Regression | Notifications | Unread/read/read all | BLQ-019 | Medium | Regression | Employee/Admin | QA | Notifications exist | Notification feed | Open feed, mark one read, mark all read. | Counts and user scoping are correct. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
PROJ-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Projects | Cost center and over-allocation ack | BLQ-011/012 | High | Regression | Admin/Project Manager | QA | Project and department setup | Allocation >100% | Select department, create allocation over 100 with acknowledgement. | Cost center autofills when configured; over-allocation requires explicit ack. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
EXP-P1-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Finance | QA Lead | Finance/Expense Regression | P1 | 3 | Sprint Regression | Expenses | Return/reject/clarification | BLQ-002/003 | High | Regression | Manager/Finance Manager/Employee | QA | Expense exists | Expense ticket | Return, resubmit, reject, add clarification. | Status and audit timeline update once without duplicate entries. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
DOC-P1-001 | Hosted QA Cycle 1 | Day 3 | 2026-06-12 | 2026-06-12 | 2026-06-12 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Documents | QA Lead | Documents/Media Regression | P1 | 2 | Sprint Regression | Documents | File validation | BLQ-013/015 | Medium | Negative | Employee/Admin | QA | Upload policy available | Oversize/wrong MIME | Upload invalid files. | Backend rejects with friendly message. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
RPT-P1-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Reports | QA Lead | Reports/Export Regression | P1 | 2 | Sprint Regression | Reports | Reports by role | BLQ-020 | Medium | Regression | Admin/Auditor/Finance Manager | QA | Report data | Report filters | Open each role report and export where allowed. | Allowed reports load; forbidden reports are blocked. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
HELP-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Helpdesk | Ticket lifecycle | BLQ-018 | Medium | Regression | Employee/Admin | QA | Helpdesk categories | Ticket | Create, comment, assign/status, resolve/reopen. | Status, comments, attachments, SLA values follow API. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ASSET-P1-001 | Hosted QA Cycle 1 | Day 4 | 2026-06-13 | 2026-06-13 | 2026-06-13 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Workflow | QA Lead | Workflow/Admin Regression | P1 | 3 | Sprint Regression | Assets | Assignment/return/recovery | BLQ-022 | Medium | Regression | Asset Manager/Admin/Employee | QA | Asset inventory | Asset | Assign asset, return, process recovery settlement. | Current recovery behavior works; payroll deduction remains future scope. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes

## Full Regression
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
AUTH-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P2 | 1 | Full Regression | Auth | Expired/used verification token | BLQ-016 | Medium | Edge | New user | QA | Token variants | Expired/used token | Open invalid token and confirm. | User-friendly error and no account verification. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
ATT-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P2 | 2 | Full Regression | Attendance | Cross-midnight work date | BLQ-007 | Medium | Edge | Employee | QA | Policy permits | Cross-midnight punch | Punch before midnight and out after midnight. | Record assigned to check-in work date in user timezone. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
HOL-P2-001 | Hosted QA Cycle 1 | Day 5 | 2026-06-14 | 2026-06-14 | 2026-06-14 20:00 IST | 2026-06-16 18:00 IST | QA Tester - HR | QA Lead | Core HR Regression | P2 | 1 | Full Regression | Holidays | Global and optional holidays | BLQ-009 | Low | Edge | Employee/HR | QA | Holiday data | All/optional holiday | Open holiday calendar and leave request around holiday. | All region is global; optional is display-only unless backend proves more. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
DOC-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Documents | QA Lead | Documents/Media Regression | P2 | 1 | Full Regression | Documents | Download after delete | BLQ-013 | Medium | Negative | Admin | QA | Deleted document | Document ID | Try download after confirmed delete. | Fails cleanly without orphaned metadata. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes
SEC-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Lead | Release Manager | Permission/Security Regression | P2 | 1 | Full Regression | Security | Production docs exposure | BLQ-023 | Medium | Security | QA Lead | Future Production | OPENAPI_PUBLIC=false | /docs URL | Open /docs and /api/v1/openapi.json. | Production does not expose docs unless intentionally configured. | Setup Required |  | Screenshot/API response/request_id |  |  | Production docs exposure check requires the future production API domain to be live. |  | Setup Required | Yes
MOB-P2-001 | Hosted QA Cycle 1 | Day 6 | 2026-06-15 | 2026-06-15 | 2026-06-15 20:00 IST | 2026-06-16 18:00 IST | QA Tester - Compatibility | QA Lead | Mobile/Cross-Browser Regression | P2 | 2 | Full Regression | Mobile | Admin table overflow | BLQ-025 | Low | Responsive | Admin | QA | Mobile viewport | Admin-heavy tables | Open employees/reports/admin tables on mobile. | No critical overlap; admin-heavy tables remain usable or documented. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes

## Rollback Checklist
Test Case ID | Sprint | Execution Day | Planned Start Date | Planned End Date | Daily Submission Due | Final Submission Due | Completion Owner | Reviewer / Signoff Owner | Execution Lane | Priority | Story Points | Suite | Feature / Module | Business Flow | Requirement / BLQ / Deployment ID | Risk | Test Type | Role / Persona | Environment | Preconditions | Test Data | Steps | Expected Result | Status | Actual Result | Evidence Required | Evidence Link / Screenshot Ref | Defect ID | Blocked Reason | Retest Due Date | Submission Status | Automation Candidate | Notes
ROLL-P1-001 | Hosted QA Cycle 1 | Day 7 | 2026-06-16 | 2026-06-16 | 2026-06-16 18:00 IST | 2026-06-16 18:00 IST | QA Lead | Product Owner | Defect Retest / Final Signoff | P1 | 2 | Rollback Checklist | Rollback | Render backend rollback | DEP-ROLLBACK | High | Process | Release Owner | QA/Production | Prior deploy exists | Render deploy | Use rollback runbook on non-prod drill. | Previous API deploy restored and health passes. | Not Run |  | Screenshot/API response/request_id |  |  |  | 2026-06-16 | Not Submitted | Yes
ROLL-P2-002 | Hosted QA Cycle 1 | Day 7 | 2026-06-16 | 2026-06-16 | 2026-06-16 18:00 IST | 2026-06-16 18:00 IST | QA Lead | Product Owner | Defect Retest / Final Signoff | P2 | 1 | Rollback Checklist | Rollback | Frontend rollback | DEP-ROLLBACK | Medium | Process | Release Owner | QA | Cloudflare history exists | Frontend deploy | Rollback QA frontend to previous deploy. | Frontend loads previous working version. | Not Run |  | Screenshot/API response/request_id |  |  |  |  | Not Submitted | Yes

## Role Permission Matrix
Role / Persona | Execution Day | Execution Lane | Submission Due | Required Permission Evidence | Expected Result | Notes
Super Admin/Admin | Day 1 | Permission/Security Regression | 2026-06-10 20:00 IST | Admin login, settings access, RBAC denial checks | Admin can configure allowed areas only in shared QA/staging | No production destructive testing
HR Manager | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | Employee, attendance, leave/WFH, EMS HR views | HR workflows are visible and scoped correctly | Use QA seed access method only
Manager/Reviewer | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | Approvals for leave/WFH/timesheet/expense where applicable | Manager can act on team items and cannot self-approve | Capture request ID for failures
Employee | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | Self-service profile, attendance, leave/WFH, timesheet | Employee cannot access admin/other employee restricted data | Mobile smoke continues Day 6
Finance Manager | Day 3 | Finance/Expense Regression | 2026-06-12 20:00 IST | Finance approval, payment, settlement, finance reports | Finance can process eligible expenses and cannot process own request | Evidence must include expense ID
Auditor | Day 5 | Reports/Export Regression | 2026-06-14 20:00 IST | Read-only reports/audit views | Auditor sees permitted data without mutation actions | No secret values in evidence
Asset Manager | Day 4 | Workflow/Admin Regression | 2026-06-13 20:00 IST | Inventory, assignment, return, recovery views | Asset workflow updates persist correctly | Capture asset ID
Helpdesk Agent/IT Support | Day 4 | Workflow/Admin Regression | 2026-06-13 20:00 IST | Ticket queue, category, SLA, assignment, lifecycle | Support actions are role-scoped | Backend role is source of truth
Release Manager | Day 6 | CI-CD/Environment Readiness | 2026-06-15 20:00 IST | CI/CD, future domain, environment isolation evidence | Future-domain gaps are documented as setup-required | No assumption that domains are live

## Business Rule Traceability
Rule ID | Source | Business Rule | Priority | Risk | Related Module | Roles Impacted | Test Case IDs | Execution Day | Execution Lane | Submission Due | Story Points | Implementation Status | Evidence Required | Blocked / Setup Reason | Notes
BLQ-001 | Business input | Role and permission management must prevent unauthorized UI and direct API access. | P0 | High | RBAC | Admin/All roles | RBAC-P0-001, EMP-P1-003 | Day 1 | Permission/Security Regression | 2026-06-10 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-002 | Business input | Expense requester must not self-process approval, finance, payment, or settlement. | P0 | High | Expenses | Employee/Manager/Finance | EXP-P0-002 | Day 3 | Finance/Expense Regression | 2026-06-12 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-003 | Business input | Expense flow is requester to manager to finance approval to payment and settlement. | P0 | High | Expenses | Employee/Manager/Finance | EXP-P0-001 | Day 3 | Finance/Expense Regression | 2026-06-12 20:00 IST | 5.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-004 | Business input | Admin policy and workflow settings are configurable by admin. | P1 | Medium | Admin settings | Admin | ADM-P1-001 | Day 5 | Workflow/Admin Regression | 2026-06-14 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-005 | Business input | Attendance punch, break, shortage, overtime, and off-day behavior must be policy-aware. | P0 | High | Attendance | Employee/Manager/HR | ATT-P0-001, ATT-P2-001 | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | 5.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-006 | Business input | Daily working hours and shortage/overtime rules are admin-policy driven. | P0 | High | Attendance | Employee/Admin | ATT-P0-001 | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-007 | Business input | Employee onboarding must create org-scoped employee data. | P0 | High | Employees | Admin/HR | ONB-P0-001, EMP-P1-001 | Day 1 | P0 Release Gate | 2026-06-10 20:00 IST | 5.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-008 | Business input | Leave balances and leave policy behavior are configurable by admin. | P1 | Medium | Leave/WFH | Employee/Manager/HR | LEAVE-P1-001 | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-009 | Business input | Holiday and off-day configuration must be visible in leave/attendance workflows. | P2 | Medium | Holidays | Employee/Admin | HOL-P2-001 | Day 5 | Core HR Regression | 2026-06-14 20:00 IST | 1.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-010 | Business input | Timesheet submission and review must support expected employee/manager workflow. | P1 | Medium | Timesheets | Employee/Manager | TIME-P1-001 | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-011 | Business input | Project creation and assignment must support allocation tracking. | P1 | Medium | Projects | Project Manager/Admin | PROJ-P1-001 | Day 4 | Workflow/Admin Regression | 2026-06-13 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-012 | Business input | Over-allocation requires explicit authorized acknowledgement if supported. | P1 | Medium | Projects | Project Manager/Admin | PROJ-P1-001 | Day 4 | Workflow/Admin Regression | 2026-06-13 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-013 | Business input | Documents must support upload, preview/open, and delete behavior. | P0 | High | Documents | Employee/Admin | DOC-P0-001, DOC-P1-001 | Day 3 | Documents/Media Regression | 2026-06-12 20:00 IST | 5.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-014 | Business input | Document delete/retention rules must be visible and verified. | P1 | Medium | Documents | Admin/Employee | DOC-P0-001 | Day 3 | Documents/Media Regression | 2026-06-12 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-015 | Business input | Cloudinary media storage must be real in hosted QA/prod, not mock fallback. | P0 | High | Documents/Media | QA Lead/Admin | CFG-P0-001, DOC-P0-001 | Day 3 | Documents/Media Regression | 2026-06-12 20:00 IST | 5.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-016 | Business input | Email verification must be explicitly confirmed by the user. | P0 | High | Auth | New user | AUTH-P0-002 | Day 1 | P0 Release Gate | 2026-06-10 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-017 | Business input | Auth/session and backend access control are release blockers. | P0 | High | Auth/RBAC | All roles | AUTH-P0-001, RBAC-P0-001 | Day 1 | P0 Release Gate | 2026-06-10 20:00 IST | 4.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-018 | Business input | Helpdesk ticket lifecycle and category/SLA behavior must be checked. | P1 | Medium | Helpdesk | Employee/Support/Admin | HELP-P1-001 | Day 4 | Workflow/Admin Regression | 2026-06-13 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-019 | Business input | Notifications must appear for key workflow events. | P1 | Medium | Notifications | All roles | NOTIF-P1-001 | Day 4 | Workflow/Admin Regression | 2026-06-13 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-020 | Business input | Reports and exports must be available to allowed roles. | P0 | Medium | Reports | Admin/Auditor/Finance/HR | RPT-P0-001, RPT-P1-001 | Day 5 | Reports/Export Regression | 2026-06-14 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-021 | Business input | EMS profile, documents, policies, letters, and HR admin flows must work. | P1 | Medium | EMS | Employee/HR | EMS-P1-001 | Day 2 | Core HR Regression | 2026-06-11 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-022 | Business input | Asset inventory, assignment, return, and recovery flows must be checked. | P1 | Medium | Assets | Asset Manager/Employee | ASSET-P1-001 | Day 4 | Workflow/Admin Regression | 2026-06-13 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-023 | Business input | Audit/report visibility must not expose unauthorized records. | P1 | Medium | Reports/Audit | Auditor/Admin | RPT-P1-001 | Day 5 | Reports/Export Regression | 2026-06-14 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-024 | Business input | New workspace must show empty real org-scoped states, not unrelated demo data. | P0 | High | Onboarding/Dashboard | Admin | ONB-P0-001 | Day 1 | P0 Release Gate | 2026-06-10 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
BLQ-025 | Business input | Critical employee flows must be usable on mobile/responsive screens. | P0 | Medium | Mobile | Employee | MOB-P0-001, MOB-P2-001 | Day 6 | Mobile/Cross-Browser Regression | 2026-06-15 20:00 IST | 3.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
DEP-DOMAIN | Deployment docs | Future hawkaii.in domains are targets only until live. | P0 | High | Environment | Release Manager/QA | DNS-P0-001, DNS-P0-002, DNS-P0-003 | Day 1 | CI-CD/Environment Readiness | 2026-06-10 20:00 IST | 3.0 | Setup Required for future-domain rows | Screenshot/API response/request ID/export/document URL as applicable | Future production hawkaii.in and api.hawkaii.in DNS/certificate setup is not live.; Future production frontend/API domain pair is not live for CORS/cookie validation.; Future QA/production domain isolation is not live. | Keep rows concise; details live in run book.
DEP-BRANCH | GitHub workflow | Branch deployments must be gated by checks and environment approval. | P0 | High | CI/CD | Release Manager | CICD-P0-001, CICD-P0-004 | Day 6 | CI-CD/Environment Readiness | 2026-06-15 20:00 IST | 2.0 | Setup Required for future-domain rows | Screenshot/API response/request ID/export/document URL as applicable | Production environment approval and production deploy target require dashboard configuration evidence. | Keep rows concise; details live in run book.
DEP-NEON | Deployment docs | Dev, QA, and production database connections must be isolated. | P0 | High | Data isolation | Release Manager | DATA-P0-001 | Day 1 | CI-CD/Environment Readiness | 2026-06-10 20:00 IST | 1.0 | Setup Required for future-domain rows | Screenshot/API response/request ID/export/document URL as applicable | Separate dev, QA, and production database connection evidence is required before isolated environment testing. | Keep rows concise; details live in run book.
DEP-CLOUDINARY | Deployment docs | Hosted QA/prod media must use real Cloudinary storage. | P0 | High | Media | QA Lead | CFG-P0-001, DOC-P0-001 | Day 3 | Documents/Media Regression | 2026-06-12 20:00 IST | 5.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.
DEP-VALKEY | Deployment docs | Dev, QA, and production Valkey/session state must be isolated. | P0 | High | Data isolation | Release Manager | DATA-P0-002 | Day 6 | CI-CD/Environment Readiness | 2026-06-15 20:00 IST | 1.0 | Setup Required for future-domain rows | Screenshot/API response/request ID/export/document URL as applicable | Separate dev, QA, and production Valkey evidence is required before isolated environment testing. | Keep rows concise; details live in run book.
DEP-MOCKS | Deployment docs | Hosted QA/prod must not use API mock fallback for signoff. | P0 | High | Environment | QA Lead | CFG-P0-001 | Day 1 | CI-CD/Environment Readiness | 2026-06-10 20:00 IST | 2.0 | Ready for QA | Screenshot/API response/request ID/export/document URL as applicable |  | Keep rows concise; details live in run book.

## Test Data
Data Area | Owner | Usage | Safety Rule
QA seed users | QA Lead | Use seeded QA/dev accounts through approved access method. | Do not paste credentials into workbook or client-facing docs.
Expense records | QA Tester - Finance | Create only in current shared QA/staging. | No production mutation.
Documents/media | QA Tester - Documents | Upload safe test files to shared QA/staging only. | Do not upload personal/sensitive files.
Future domains | Release Manager | Use only for readiness checks after domains are live. | Keep setup-required until evidence exists.

## Defect Log
Defect ID | Test Case ID | Severity | Priority | Title | Steps | Expected | Actual | Evidence Link / Screenshot Ref | Request ID | Owner | Status | Report Due | Retest Due Date | SLA Rule
|  | Critical/P0 | P0 | [8 empty] | Immediate | Same day when fixed | Any failed P0 must appear in release signoff summary.
|  | High/P1 | P1 | [8 empty] | Same day | Next execution day | Retest by next execution day when fixed.
|  | Medium/P2 | P2 | [8 empty] | By daily cutoff | By final day if included | Include open P2 in final risk summary if not fixed.

## Future Scope
Item | Reason | Priority
Isolated production, QA, and hosted dev domain execution | Future domains/services are documented but not live for this cycle. | P0 setup dependency
Production destructive testing | Requires documented safe production tenant and reset process. | P0 safety dependency
Automation expansion | Manual first full QA cycle is the priority; automate stable P0/P1 paths after signoff. | P1
Performance/load testing | Out of scope for strict first 7-day hosted QA unless a blocker appears. | P2

## Signoff
Field | Value | Rule / Notes
Planned QA start date | 2026-06-10 | 09:00 IST
Planned completion date | 2026-06-16 | All execution rows close by final day
Final submission date/time | 2026-06-16 18:00 IST | Final signoff package due
Total cases | 51 | Executable test cases
Total P0 | 28 | Release/client signoff blockers
Total P1 | 16 | Important regression
Total P2 | 7 | Deep regression/future readiness
Completed | 0 | Updated during execution
Passed | 0 | Updated during execution
Failed | 0 | Any failed P0 means No-Go unless waived
Blocked | 16 | Includes setup-required future-domain/environment rows
Not run | 35 | Rows awaiting execution
P0 pass rate | 0% | Pass count / total P0
P1 pass rate | 0% | Pass count / total P1
Release recommendation | Conditional Go | Go / Conditional Go / No-Go
Open risk summary | Future domain and isolated environment checks remain setup-required; execute release gate on current shared hosted QA/staging only. | Future-domain setup is not a pass condition for current shared QA/staging
Signoff owner | Product Owner / Release Manager | Final approval owner
Signoff date | 2026-06-16 | Target signoff date